## Executive_Summary
Construction Project Controls - Act Phase
Recommended decision: approve a 90-day Project Controls Recovery and Automation Program focused on the highest-risk projects, control governance, Power BI automation, and a governed In Project AI pilot.
Portfolio BAC |  |  | Forecast EAC |  | Forecast Overrun | Red Projects
5831436600 |  |  | 6586989965.6969 |  | 12.96% | 50
Weighted CPI |  |  | Weighted SPI |  | Average Delay | Contingency Used
0.88417 |  |  | 0.98717 |  | 33.68 | 66.23%
30 / 60 / 90-Day Decision Roadmap
First 30 Days | Days 31-60 | Days 61-90 | Decision Gate | Proposed Management Outcomes
Review top-10 projects | Publish Power BI | Build Python risk pilot | Pilot evaluation | 100% of top-10 projects have intervention owners and recovery plans.
Revalidate EAC | Schedule refresh | Create prediction table | Security validation | Every contingency drawdown is linked to an approved risk or change.
Approve schedule recovery | Refresh-failure alerts | Connect In Project AI | User acceptance | High/Critical RFI on-time response reaches at least 90%.
Control contingency | Red-project alerts | Test answer traceability | Business case | Approved changes are incorporated into forecasts within 5 business days.
RFI closure sprint | Read-only reporting views | Audit logs | Go / Revise / Stop | Power BI refresh success reaches at least 98%.
Change-control board | Refresh runbook | Model documentation | Fabric decision | All AI numerical answers include a governed source and reporting date.
Important: these are proposed operating targets for a synthetic demonstration portfolio. They are not achieved results and must be adapted to actual contracts, client processes, risk tolerance, security requirements, and data availability.

## Action_Register
90-Day Action Register
Action ID | Workstream | Priority | Timing | Start Date | Target Date | Owner | Support | Action | Evidence | Deliverable | Success Metric | Status | Days Remaining | Schedule Status | Management Notes
A01 | Executive Intervention | Critical | Days 1-3 | 2026-07-30 | 2026-08-01 | Executive Sponsor | Project Controls Lead; Project Managers | Convene a portfolio exception review for the 10 highest-priority projects. | Top 10 ranked Red projects; 50 Red projects across the portfolio. | Signed intervention register with accountable owner and next review date for each project. | 100% of top 10 projects assigned an intervention owner within 3 business days. | Not Started | 2 | On Track
A02 | Cost Recovery | Critical | Days 1-10 | 2026-07-30 | 2026-08-08 | Cost Manager | Project Manager; Project Controls Lead | Revalidate estimate to complete, remaining commitments, productivity assumptions, accruals, and buyout exposure on every top-10 project. | Portfolio weighted CPI 0.884; forecast overrun 13.0%. | Project-level cost recovery sheet and approved revised EAC. | 100% of top-10 EACs independently reviewed; unexplained variance below 2% of BAC. | Not Started | 9 | On Track
A03 | Schedule Recovery | Critical | Days 1-14 | 2026-07-30 | 2026-08-12 | Scheduler | Project Manager; Superintendent; Design Manager | Perform critical-path, near-critical-path, constraint, procurement, and 6-week look-ahead review for top-10 projects. | Average forecast delay 33.7 days despite weighted SPI 0.987. | Schedule recovery plan with logic corrections, constraints, responsible parties, and milestone impacts. | 100% of top-10 projects have an approved recovery or mitigation plan within 14 days. | Not Started | 13 | On Track
A04 | Contingency Governance | Critical | Days 1-14 | 2026-07-30 | 2026-08-12 | Project Controls Lead | Cost Manager; Executive Sponsor | Require approval and risk linkage for new contingency drawdowns; review projects using contingency faster than physical progress. | Contingency burn ratio had the strongest tested relationship with forecast overrun (r = 0.901). | Contingency drawdown register with risk reference, approval, remaining balance, and burn ratio. | 100% of new contingency use linked to an approved risk/change; burn ratio reviewed weekly. | Not Started | 13 | On Track
A05 | RFI Recovery | High | Days 1-21 | 2026-07-30 | 2026-08-19 | Design Manager | Project Managers; Discipline Leads | Run an RFI closure sprint focused on overdue, High, and Critical RFIs, especially Electrical and Structural disciplines. | Average RFI response 14.6 days; late-response rate 75.2%; response time associated with schedule delay (r = 0.517). | Prioritized RFI aging log and daily closure report until backlog is controlled. | Reduce average response time to 10 days or less and achieve at least 90% on-time response for High/Critical RFIs. | Not Started | 20 | On Track
A06 | Change Control | High | Days 1-30 | 2026-07-30 | 2026-08-28 | Change Control Board | Owner Representative; Designer; Contractor | Establish weekly change triage for owner-directed changes, design errors/omissions, and unforeseen conditions. | Approved change value $151,618,700; pending exposure $30,891,200. | Weekly change dashboard showing age, cause, cost, schedule impact, decision, and forecast incorporation. | 100% of approved changes incorporated into current budget and forecast within 5 business days. | Not Started | 29 | On Track
A07 | Forecast Governance | High | Days 15-30 | 2026-08-13 | 2026-08-28 | Project Controls Lead | Cost Managers; Schedulers; Project Managers | Introduce monthly forecast certification and a documented reason code for material EAC or completion-date changes. | High Red-project concentration and material cost/schedule exposure require repeatable forecast governance. | Forecast certification checklist and variance reason-code standard. | 100% of monthly forecasts certified; all changes above 2% BAC or 10 days explained. | Not Started | 29 | On Track
A08 | Power BI Automation | High | Days 15-45 | 2026-08-13 | 2026-09-12 | Data Analyst | Power BI Owner; IT Administrator | Move source files to a governed OneDrive/SharePoint folder or reporting database, publish the report, configure scheduled refresh, and test refresh history. | Current CSV-based dashboard is ready; automation removes repeated manual imports. | Published semantic model with refresh schedule, credentials, owner, and recovery procedure. | At least 98% successful scheduled refreshes and data available before the weekly controls meeting. | Not Started | 44 | On Track
A09 | Automated Alerts | High | Days 30-50 | 2026-08-28 | 2026-09-17 | Data Analyst | Power Automate Owner; Project Controls Lead | Create refresh-failure alerts and a filtered Power Automate action for Red projects, new threshold breaches, or overdue High/Critical RFIs. | Exception-based workflow is needed to convert dashboard insight into action. | Tested email/Teams alert flow with recipients, escalation rules, and audit log. | Alert delivered within 30 minutes of refresh completion or failure; no unauthorized project data in messages. | Not Started | 49 | On Track
A10 | Predictive Analytics Pilot | Medium | Days 45-75 | 2026-09-12 | 2026-10-12 | Data Analyst / Model Owner | Project Controls SME | Develop a versioned Python risk model or rules-based pilot that writes cost-overrun probability, delay probability, and top risk drivers to a prediction table. | Contingency burn and RFI response time provide useful candidate predictive features. | Model card, evaluation report, prediction table, and monitoring thresholds. | Reproducible run; documented precision/recall or error metrics; every prediction includes model version and date. | Not Started | 74 | On Track
A11 | In Project AI Integration | Medium | Days 60-90 | 2026-09-27 | 2026-10-27 | In Project AI Product Owner | Developer; Data Analyst; Security Owner | Connect approved project metrics and predictions to the In Project AI agent through read-only governed tools. | The agent can explain project condition only when it retrieves authorized, dated metrics. | Agent tools for portfolio summary, project explanation, risk drivers, and dashboard link. | 100% of numerical answers include source table/reporting date; zero cross-client data leakage in tests. | Not Started | 89 | On Track
A12 | Pilot and Scale Decision | Medium | Days 75-90 | 2026-10-12 | 2026-10-27 | Executive Sponsor | Product Owner; Finance; Security; Pilot Client | Run a controlled pilot and decide whether client demand justifies Fabric, Power BI Embedded, additional connectors, and multi-tenant controls. | Enterprise architecture should follow demonstrated value, security readiness, and recurring revenue. | Pilot evaluation and formal Go / Revise / Stop decision. | Pilot user acceptance, measurable time savings, verified security controls, and approved business case. | Not Started | 89 | On Track
Formulas:
Days Remaining = [Target Date]-TODAY()
Schedule Status = IF([Status]="Complete","Complete",IF([Target Date]<TODAY(),"Overdue","On Track"))

## Governance_Cadence
Project Controls Governance Cadence
Frequency | Forum | Accountable Owner | Required Agenda | Primary Output
Daily during recovery | Top-10 exception stand-up | Project Manager | Critical constraints, new risks, overdue RFIs, immediate decisions | Top-10 recovery log
Weekly | Portfolio controls review | Project Controls Lead | Red/Yellow status, CPI/SPI, EAC, delay, contingency burn, change/RFI exceptions | Executive dashboard and action register
Weekly | Change Control Board | Owner/Executive Sponsor | Pending changes, approval aging, cost/schedule impact, forecast incorporation | Change decision log
Weekly | RFI aging review | Design Manager | High/Critical RFIs, overdue responses, discipline bottlenecks | RFI aging dashboard
Monthly | Forecast certification | Project Controls Lead | EAC, ETC, completion date, reason codes, assumptions | Certified forecast package
Monthly | Data quality and refresh review | Data Analyst | Refresh failures, schema changes, missing data, metric reconciliation | Data quality report
Quarterly | Model and AI governance | Model Owner / Security Owner | Model drift, answer accuracy, access controls, audit logs | Model card update and AI control report

## KPI_Targets
Proposed Recovery and Automation KPIs
Metric | Proposed Target | Review Frequency | Owner | Interpretation
Top-10 intervention coverage | 100% | Within 3 business days | Executive Sponsor | Proposed operating target
Red project weekly review coverage | 100% | Weekly | Project Controls Lead | Proposed operating target
Weighted CPI | Improve by at least 0.02 over 90 days | Monthly | Cost Managers | Portfolio recovery target; not guaranteed
Average forecast delay | Reduce by at least 10 days over 90 days | Monthly | Schedulers | Portfolio recovery target; not guaranteed
Contingency drawdown traceability | 100% | Weekly | Project Controls Lead | Every draw linked to approved risk/change
Contingency burn ratio | ≤1.20x for projects not classified Red | Weekly | Project Manager | Approved portfolio threshold
High/Critical RFI on-time response | ≥90% | Weekly | Design Manager | Proposed SLA target
Average RFI response time | ≤10 days | Weekly | Design Manager | Proposed SLA target
Approved changes incorporated into forecast | 100% within 5 business days | Weekly | Cost Manager | Proposed control target
Power BI scheduled refresh success | ≥98% | Weekly | Data Analyst | Automation reliability target
AI numerical answer traceability | 100% | Monthly | Product Owner | Source/reporting date required
Cross-client data leakage | 0 events | Continuous | Security Owner | Non-negotiable control

## Top_10_Projects
Top 10 Projects for Immediate Intervention
Rank | Project ID | Project Name | Type | CPI | SPI | Forecast Overrun | Delay Days | Contingency Used | Primary Driver | All Triggers
1 | PRJ-075 | Canyon Ridge Transit-Oriented Development | Mixed-Use | 0.75261 | 0.99717 | 32.87% | 73 | 107.1% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
2 | PRJ-009 | Northstar Housing | Residential | 0.75479 | 1 | 32.49% | 63 | 105.6% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
3 | PRJ-046 | Red Rock Residences | Residential | 0.77901 | 1 | 28.37% | 84 | 107.1% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
4 | PRJ-068 | Canyon Ridge Bridge Rehabilitation | Heavy Civil & Infrastructure | 0.79426 | 1 | 25.9% | 55 | 95.45% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
5 | PRJ-034 | Mountain Gate Community College | Institutional | 0.80532 | 1 | 24.17% | 38 | 91.35% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
6 | PRJ-017 | Westfield Retail Center | Commercial | 0.8136 | 0.98793 | 22.91% | 48 | 91.57% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
7 | PRJ-064 | Evergreen Townhomes | Residential | 0.81579 | 1 | 22.58% | 34 | 92.45% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
8 | PRJ-013 | Sunrise Housing | Residential | 0.81926 | 1 | 22.06% | 61 | 91.72% | CPI < 0.90 | CPI < 0.90; Forecast overrun > 10%; Delay > 30 days; Contingency used > 90%
9 | PRJ-069 | Cedar Valley Town Center | Mixed-Use | 0.84916 | 0.84762 | 17.76% | 104 | 61.12% | CPI < 0.90 | CPI < 0.90; SPI < 0.90; Forecast overrun > 10%; Delay > 30 days
10 | PRJ-025 | Blue Mesa Public Safety Center | Institutional | 0.89271 | 0.86887 | 12.02% | 87 | 33.05% | CPI < 0.90 | CPI < 0.90; SPI < 0.90; Forecast overrun > 10%; Delay > 30 days

## Automation_Plan
Automation Path for Power BI, Tableau, Python, and In Project AI
Level | Architecture | Automates | Manual Work Remaining | Typical Use | Decision Trigger | Official Reference
1 - Local | Windows Task Scheduler + Python + CSV | Validation, alert files, scoring outputs, logs | Power BI Desktop refresh and publish | Portfolio/demo | Start immediately | https://learn.microsoft.com/en-us/power-bi/connect-data/refresh-data
2 - Power BI Cloud | OneDrive/SharePoint + Power BI Service + Power Automate | Scheduled refresh, refresh alerts, contextual workflow actions | Report design and governance | First client/pilot | Need sharing and recurring refresh | https://learn.microsoft.com/en-us/power-bi/connect-data/refresh-scheduled-refresh
3 - Database + AI | Supabase/PostgreSQL + scheduled Python/Azure Function + Power BI | Data refresh, predictions, exception outputs, agent retrieval | Model review and security governance | Live reporting | Need governed client data | https://learn.microsoft.com/en-us/power-bi/create-reports/power-bi-automate-visual
4 - Fabric | Fabric Data Factory + Notebook + semantic model + alerts | Pipelines, schedules, event triggers, notebooks, monitoring | Enterprise architecture and cost governance | Enterprise scale | Several connectors or Microsoft governance requirement | https://learn.microsoft.com/en-us/fabric/data-factory/pipeline-runs
Tableau option | Tableau Cloud/Server + Extracts or Bridge | Scheduled extract refresh and live private-network queries | Workbook authoring and permissions | Public portfolio or Tableau client | Client uses Tableau | https://help.tableau.com/current/online/en-us/to_bridge_faq.htm

## Sources
Official Automation References
Source | URL | Use
Power BI data refresh | https://learn.microsoft.com/en-us/power-bi/connect-data/refresh-data | Scheduled/on-demand refresh, OneDrive synchronization, limits
Power BI scheduled refresh | https://learn.microsoft.com/en-us/power-bi/connect-data/refresh-scheduled-refresh | Credentials, gateway, schedule settings
Power Automate visual | https://learn.microsoft.com/en-us/power-bi/create-reports/power-bi-automate-visual | Contextual flow launched from a report
Power BI pricing | https://www.microsoft.com/en-us/power-platform/products/power-bi/pricing | Free authoring and Pro/PPU pricing
Fabric pipeline schedules | https://learn.microsoft.com/en-us/fabric/data-factory/pipeline-runs | On-demand, scheduled, and event-based pipeline runs
Fabric job scheduler | https://learn.microsoft.com/en-us/fabric/fundamentals/job-scheduler | Recurring supported Fabric jobs
Tableau Cloud refresh | https://help.tableau.com/current/online/en-us/schedule_add.htm | Scheduled extract refresh
Tableau Bridge | https://help.tableau.com/current/online/en-us/to_bridge_faq.htm | Private-network file/database refresh and live queries