## Overview
Construction Project Controls Analytics — Data Dictionary
Synthetic dataset for a Google Data Analytics capstone, professional portfolio, and In Project LLC demonstration. The raw files intentionally contain realistic data-quality issues for the Process phase.
Dataset Version | 1.0
Generation Seed | 3404
Currency | U.S. dollars
Reporting Period | 2022-01-01 through 2025-12-31
Intended Unique Projects | 75
Data Classification | Synthetic / educational / portfolio demonstration
Primary Relationship Key | Project_ID
File / Table | Intended Grain | Raw Rows | Intended Base Rows | Primary Key | Relationship
projects_raw.csv | One row per intended project | 77 | 75 | Project_ID | Parent table
monthly_performance_raw.csv | One row per project/reporting month | 1747 | 1743 | Performance_Record_ID | Many-to-one with Projects
change_orders_raw.csv | One row per change order | 557 | 554 | Change_Order_ID | Many-to-one with Projects
rfi_log_raw.csv | One row per RFI | 1518 | 1515 | RFI_ID | Many-to-one with Projects
Relational Model
PROJECTS
Project_ID (PK)
MONTHLY PERFORMANCE | Project_ID (FK) | → | 1 | ← | Project_ID (FK) | CHANGE ORDERS
RFI LOG | Project_ID (FK) | → | 1 | ← | Project_ID (FK)
Parent table
Prepare-Phase Decision | Selected Approach
Data source | Realistic synthetic construction project-controls data
Reason | Public data rarely includes monthly EV, PV, AC, contingency, change orders, and RFIs in one usable model.
Privacy | No real client, employee, contract, or confidential project data.
Next phase | Profile, clean, validate, and document transformations without editing raw files.

## Projects
Projects — Field Definitions
Field Name | Data Type | Description | Example | Nullable? | Validation Rule | Analytical Use | Source / Generation
Project_ID | Text | Unique construction project identifier. | PRJ-001 | No | Unique after cleaning; pattern PRJ-###. | Primary key and table joins. | Synthetic sequence
Project_Name | Text | Fictional project name. | Canyon Ridge Medical Center | No | Trim whitespace; project name should be readable. | Labels and project-level reporting. | Synthetic name
Project_Type | Category | Construction sector classification. | Institutional | No | Must map to the approved project-type code list. | Segment cost and schedule performance. | Weighted synthetic category
City | Text | Fictional project city. | Lehi | No | Nonblank text. | Geographic analysis. | Synthetic assignment
State | Category | Two-letter U.S. state abbreviation. | UT | No | Approved two-letter code list. | Geographic filtering. | Synthetic assignment
Client_Type | Category | Public or private client classification. | Public | No | Public or Private. | Compare client segments. | Synthetic category
Contract_Type | Category | Commercial contract arrangement. | Guaranteed Maximum Price | Yes | Approved code list; investigate blanks. | Compare contract performance. | Synthetic category
Delivery_Method | Category | Project delivery approach. | CMAR | No | Approved code list. | Compare delivery-method performance. | Synthetic category
Project_Manager_ID | Text | Anonymous project manager identifier. | PM-004 | No | Pattern PM-###. | Portfolio segmentation without personal names. | Synthetic assignment
Original_Budget | Currency | Initial approved project budget. | 45000000 | No | Numeric and greater than 0. | BAC baseline and project-size analysis. | Synthetic financial value
Current_Budget | Currency | Current authorized budget including approved changes. | 46850000 | No | Numeric; normally at least original budget. | Budget growth and current authorization. | Derived from approved changes
Original_Contingency | Currency | Initial contingency allowance. | 3150000 | No | Numeric and nonnegative. | Contingency utilization analysis. | Synthetic percentage of budget
Start_Date | Date | Project start date. | 2022-03-14 | No | Valid date; before planned end. | Duration and time-series alignment. | Synthetic date
Planned_End_Date | Date | Baseline planned completion date. | 2024-06-14 | No | Valid date after start. | Baseline schedule comparison. | Synthetic baseline
Forecast_End_Date | Date | Latest forecast completion date. | 2024-08-01 | No | Valid date; compare with planned end. | Forecast schedule delay. | Derived synthetic forecast
Project_Status | Category | Latest portfolio status. | Active | No | Planning, Active, On Hold, or Complete. | Status filtering and portfolio reporting. | Derived status
Current_Phase | Category | Latest project lifecycle phase. | Construction | No | Planning, Design, Procurement, Construction, Closeout. | Phase-based comparisons. | Derived from progress
Percent_Complete | Percentage | Latest reported physical progress. | 72.4 | No | Numeric from 0 through 100. | Progress and burn-rate comparisons. | Latest performance record

## Monthly_Performance
Monthly Performance — Field Definitions
Field Name | Data Type | Description | Example | Nullable? | Validation Rule | Analytical Use | Source / Generation
Performance_Record_ID | Text | Unique monthly performance-record identifier. | PERF-000125 | No | Unique pattern PERF-######. | Primary key. | Synthetic sequence
Project_ID | Text | Parent construction project identifier. | PRJ-006 | No | Must exist in Projects. | Relationship to project attributes. | Foreign key
Reporting_Date | Date | Monthly status date. | 2024-05-31 | No | Valid month-end date within reporting period. | Time-series analysis. | Monthly calendar
Planned_Value | Currency | Cumulative budgeted value of scheduled work. | 18400000 | No | Numeric, nonnegative, generally nondecreasing. | SPI and schedule variance. | Synthetic S-curve
Earned_Value | Currency | Cumulative budgeted value of performed work. | 17150000 | No | Numeric, nonnegative, generally nondecreasing. | CPI, SPI, CV, and SV. | Progress-based generation
Actual_Cost | Currency | Cumulative actual cost of performed work. | 17950000 | Yes | Numeric and nonnegative; investigate blanks or outliers. | CPI, CV, and forecasting. | Cost-efficiency model
Percent_Complete | Percentage | Cumulative physical progress at the report date. | 45.7 | No | Numeric from 0 through 100. | Progress trends and normalization. | Progress model
Committed_Cost | Currency | Cumulative contracted or committed cost. | 28200000 | No | Numeric; at least actual cost in normal conditions. | Cost exposure and forecast review. | Forecast-based generation
Contingency_Used | Currency | Cumulative contingency consumed. | 780000 | No | Numeric, nonnegative, generally nondecreasing. | Contingency utilization and burn ratio. | Risk/change model
Forecast_End_Date | Date | Completion forecast at the reporting date. | 2024-08-01 | No | Valid date; may change across months. | Schedule-forecast trend. | Progressive forecast
Open_RFI_Count | Integer | RFIs unresolved at the reporting date. | 12 | No | Whole number and nonnegative. | RFI backlog analysis. | Derived from RFI events
Pending_CO_Value | Currency | Value of pending changes at the reporting date. | 430000 | No | Numeric and nonnegative. | Potential unapproved exposure. | Derived from change orders
Approved_CO_Value | Currency | Cumulative approved-change value at the reporting date. | 1250000 | No | Numeric, nonnegative, generally nondecreasing. | Change exposure and budget growth. | Derived from change orders

## Change_Orders
Change Orders — Field Definitions
Field Name | Data Type | Description | Example | Nullable? | Validation Rule | Analytical Use | Source / Generation
Change_Order_ID | Text | Unique change-order identifier. | CO-00125 | No | Unique pattern CO-#####. | Primary key. | Synthetic sequence
Project_ID | Text | Parent construction project identifier. | PRJ-014 | No | Must exist in Projects. | Relationship to project attributes. | Foreign key
Change_Title | Text | Short fictional description of the change. | Utility Conflict - Civil package | No | Trim whitespace. | Display and qualitative review. | Synthetic description
Change_Category | Category | Primary cause of the change. | Unforeseen Condition | No | Must map to approved category list. | Root-cause segmentation. | Weighted synthetic category
Responsible_Party | Category | Party primarily associated with the change. | External | No | Owner, Designer, Contractor, or External. | Responsibility segmentation. | Category mapping
Submitted_Date | Date | Date the change was submitted. | 2023-08-12 | No | Valid date; not after approved date. | Approval-cycle calculation. | Synthetic event date
Approved_Date | Date | Date the change was approved. | 2023-09-19 | Yes | Required for approved changes; blank otherwise. | Approval-cycle calculation. | Synthetic event date
Submitted_Value | Currency | Requested change value. | 485000 | No | Numeric and nonnegative. | Requested exposure analysis. | Budget-scaled generation
Approved_Value | Currency | Authorized change value. | 447000 | Yes | Required for approved changes; blank otherwise. | Budget growth and approved exposure. | Derived from requested value
Schedule_Impact_Days | Integer | Approved or estimated schedule impact. | 9 | No | Whole number and nonnegative. | Delay-impact analysis. | Category/risk model
Change_Status | Category | Current change-order status. | Approved | No | Approved, Pending, Rejected, or Withdrawn. | Workflow and exposure filtering. | Weighted synthetic status
Discipline | Category | Technical discipline associated with the change. | Civil | No | Must map to discipline code list. | Discipline-level analysis. | Synthetic category

## RFI_Log
RFI Log — Field Definitions
Field Name | Data Type | Description | Example | Nullable? | Validation Rule | Analytical Use | Source / Generation
RFI_ID | Text | Unique request-for-information identifier. | RFI-00345 | No | Unique pattern RFI-#####. | Primary key. | Synthetic sequence
Project_ID | Text | Parent construction project identifier. | PRJ-022 | No | Must exist in Projects. | Relationship to project attributes. | Foreign key
RFI_Title | Text | Short fictional RFI description. | Mechanical clarification item 345 | No | Trim whitespace. | Display and qualitative review. | Synthetic description
Discipline | Category | Technical discipline associated with the RFI. | Mechanical | No | Must map to discipline code list. | Discipline segmentation. | Weighted synthetic category
Submitted_Date | Date | Date the RFI was issued. | 2024-02-03 | No | Valid date; before response date. | Response-cycle calculation. | Synthetic event date
Required_Response_Date | Date | Contractual or target response date. | 2024-02-10 | No | Valid date on or after submission. | Late-response classification. | Priority-based target
Response_Date | Date | Actual response date. | 2024-02-16 | Yes | May be blank for open RFIs; required when answered or closed. | Response-cycle calculation. | Synthetic event date
RFI_Status | Category | Current workflow status. | Answered | No | Open, Answered, Closed, or Void if later introduced. | Backlog and workflow analysis. | Synthetic status
Response_Days | Integer | Elapsed days from submission to response. | 13 | Yes | Whole number; blank for open RFIs. | Average response-time analysis. | Derived duration
Responsible_Party | Category | Party responsible for the response. | Designer | No | Owner, Designer, Contractor, or External. | Responsibility segmentation. | Weighted synthetic category
Cost_Impact | Currency | Estimated or confirmed cost impact. | 18000 | No | Numeric and nonnegative. | Impact analysis. | Probabilistic synthetic impact
Schedule_Impact_Days | Integer | Estimated schedule impact. | 3 | No | Whole number and nonnegative. | Delay-impact analysis. | Probabilistic synthetic impact
Priority | Category | RFI priority. | High | No | Low, Normal, High, or Critical. | Response-time service-level analysis. | Weighted synthetic priority

## Validation_Rules
Data Integrity and Validation Rules
Table | Rule ID | Field(s) | Rule | Expected Handling | Severity
Projects | PRJ-01 | Project_ID | Unique after cleaning and pattern PRJ-###. | Remove or reconcile duplicates; document treatment. | Critical
Projects | PRJ-02 | Dates | Start_Date < Planned_End_Date; forecast date must be valid. | Standardize and validate dates. | Critical
Projects | PRJ-03 | Budget fields | Numeric and greater than or equal to zero; Original_Budget > 0. | Strip symbols/commas and convert to numeric. | Critical
Monthly Performance | PERF-01 | Project_ID + Reporting_Date | No more than one row per project per reporting month. | Identify and remove true duplicates. | Critical
Monthly Performance | PERF-02 | Project_ID | Must exist in Projects. | Trim and validate foreign keys. | Critical
Monthly Performance | PERF-03 | PV/EV/AC | Numeric and nonnegative; cumulative values should generally not decrease. | Investigate missing values and outliers. | Critical
Monthly Performance | PERF-04 | Percent_Complete | Numeric from 0 through 100. | Remove percent signs and validate range. | High
Change Orders | CO-01 | Change_Order_ID | Unique after cleaning. | Remove or reconcile duplicates. | Critical
Change Orders | CO-02 | Project_ID | Must exist in Projects. | Validate foreign-key relationship. | Critical
Change Orders | CO-03 | Approved records | Approved_Date and Approved_Value required when status is Approved. | Investigate and document missing approval data. | High
Change Orders | CO-04 | Date sequence | Approved_Date cannot precede Submitted_Date. | Correct only with documented evidence; otherwise flag/exclude. | Critical
RFI Log | RFI-01 | RFI_ID | Unique after cleaning. | Remove or reconcile duplicates. | Critical
RFI Log | RFI-02 | Project_ID | Must exist in Projects. | Trim and validate foreign keys. | Critical
RFI Log | RFI-03 | Response logic | Open RFIs may be blank; Answered/Closed RFIs require response data. | Classify legitimate vs erroneous missing values. | High
RFI Log | RFI-04 | Date sequence | Response_Date cannot precede Submitted_Date. | Flag and investigate. | Critical

## Code_Lists
Approved Categorical Values
List Name | Approved Value | Definition
Project_Type | Residential | Approved construction-sector label.
Project_Type | Commercial | Approved construction-sector label.
Project_Type | Institutional | Approved construction-sector label.
Project_Type | Industrial | Approved construction-sector label.
Project_Type | Heavy Civil & Infrastructure | Approved construction-sector label.
Project_Type | Mixed-Use | Approved construction-sector label.
Contract_Type | Lump Sum | Approved contract-type label.
Contract_Type | Guaranteed Maximum Price | Approved contract-type label.
Contract_Type | Cost Plus | Approved contract-type label.
Contract_Type | Unit Price | Approved contract-type label.
Delivery_Method | Design-Bid-Build | Approved delivery-method label.
Delivery_Method | Design-Build | Approved delivery-method label.
Delivery_Method | CMAR | Approved delivery-method label.
Delivery_Method | Integrated Project Delivery | Approved delivery-method label.
Project_Status | Planning | Approved project-status label.
Project_Status | Active | Approved project-status label.
Project_Status | On Hold | Approved project-status label.
Project_Status | Complete | Approved project-status label.
Current_Phase | Planning | Approved project-phase label.
Current_Phase | Design | Approved project-phase label.
Current_Phase | Procurement | Approved project-phase label.
Current_Phase | Construction | Approved project-phase label.
Current_Phase | Closeout | Approved project-phase label.
Discipline | Architectural | Approved technical-discipline label.
Discipline | Civil | Approved technical-discipline label.
Discipline | Structural | Approved technical-discipline label.
Discipline | Mechanical | Approved technical-discipline label.
Discipline | Electrical | Approved technical-discipline label.
Discipline | Plumbing | Approved technical-discipline label.
Discipline | Fire Protection | Approved technical-discipline label.
Discipline | General | Approved technical-discipline label.
Change_Status | Approved | Approved change-order status.
Change_Status | Pending | Approved change-order status.
Change_Status | Rejected | Approved change-order status.
Change_Status | Withdrawn | Approved change-order status.
RFI_Status | Open | Approved RFI status.
RFI_Status | Answered | Approved RFI status.
RFI_Status | Closed | Approved RFI status.
Priority | Low | Approved RFI priority.
Priority | Normal | Approved RFI priority.
Priority | High | Approved RFI priority.
Priority | Critical | Approved RFI priority.
Change_Category | Owner-Directed Change | Approved change-order cause category.
Change_Category | Design Error or Omission | Approved change-order cause category.
Change_Category | Unforeseen Condition | Approved change-order cause category.
Change_Category | Scope Clarification | Approved change-order cause category.
Change_Category | Code or Regulatory Requirement | Approved change-order cause category.
Change_Category | Material Substitution | Approved change-order cause category.
Change_Category | Contractor-Requested Change | Approved change-order cause category.
Change_Category | Coordination Issue | Approved change-order cause category.
Change_Category | Weather Impact | Approved change-order cause category.
Change_Category | Utility Conflict | Approved change-order cause category.

## Data_Quality_Plan
Raw Data Quality Plan for the Process Phase
Issue Category | Why It Is Included | Detection Approach | Treatment Principle
Duplicates | Realistic export or entry duplication. | Primary-key counts and duplicate combinations. | Retain one valid record; document removal logic.
Whitespace/case | Common manual-entry inconsistency. | TRIM, distinct-value review, category frequency. | Standardize to approved code lists.
Mixed dates | Common CSV and regional-format problem. | Parse tests and invalid-date review. | Convert to ISO date after validation.
Currency as text | Symbols and commas prevent calculations. | Type profiling and failed numeric conversions. | Strip symbols/commas and convert to numeric.
Percent as text | Percent sign causes mixed data types. | Type profiling and range validation. | Remove sign; store consistently as 0–100.
Missing values | May be legitimate or erroneous. | Null counts by status and business rule. | Classify before imputing or excluding.
Invalid foreign keys | Breaks relational joins. | Anti-join child Project_ID values to Projects. | Correct only when evidence exists; otherwise flag/exclude.
Illogical dates | Possible entry or extraction errors. | Compare submitted and response/approval dates. | Flag; do not silently overwrite.
Numerical outlier | Could be a true extreme or data error. | Distribution review, ratios, project trend inspection. | Investigate context before exclusion.